## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action | Guidelines
Example : All tasks were completed on time. Team communication was seamless. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Example
The prediction model gave accurate results in most test cases. | Original Plan for MongoDB Database changed due to System Incompatability and Failures | Validate datasets before sprint start. | Set stricter deadlines for finalizing requirements. | Ensure all datasets are verified and cleaned before sprint planning begins.
The web pages were compatible and consistent when being used with different devices and browsers | Realtime Alerts were scrapped | Add onboarding tooltip or help guide for graphs. | Include a data validation checkpoint before model training. | Make UI/UX enhancements user-centric with visual cues and onboarding elements.
The Front End Design was well received by colleagues | Password Recovery was removed due to less importance | Expand chatbot training with regional crop data. | Collect FAQs from users and integrate them into chatbot training. | Use localized datasets and feedback loops to continuously train NLP models.
Chatbot Service was added and created in sufficient time | Graphs were initially not downloading and showing in Web Page | Create React or NodeJS based Application for better overall look | Implement a short walkthrough or "?" icons for first-time users.
Minimal Bugs were detected | Multiple Roles were to be defined, but instead we were limited to Admin and User with minimal differentiating factors due to operational complexity and time constraints | Add various unique roles like Analyst, Seller, etc,
Collaboration in both offline and online mode was fruitful and efficient |  | Expand upon Admin Functionality
Initially Graphs were made to be static but they were updated to be Reactive, ie we can now observe each point and observe their details
Crop Recommendation Module was added and gives accurate outputs for multiple different cases